## Sheet1
ACTION LOG FOR TEAM
| Name(s) | Date Range | Hours Worked | Task | Comments/Notes
| Stephanie, Daniel, Rebecca, Taylor, Moises | September 21st, 2021 | 1 | Prepared Questions for Sponsor Meeting
| Stephanie, Daniel, Rebecca, Taylor, Moises | September 22nd, 2021 | 0.5 | First Sponsor Meeting w/ Tim | Met Tim and asked clarifying questions about Amazon's expectations for this project
| Stephanie, Daniel, Rebecca, Taylor, Moises | September 26th, 2021 | 1 | Weekly Meeting | Work on Gantt Chart, built Action logs, assigned research tasks, discussed future work
| Stephanie, Daniel, Rebecca, Taylor, Moises | September 28th, 2021 | 1 | Meeting for First TED Talk | Met to work on Project Defintion TED talk presentation
| Stephanie, Daniel, Rebecca, Taylor, Moises | September 29th, 2021 | 0.5 | Project Definition TED Talk | Presented to our section slides depicting our project defintion
| Stephanie, Daniel, Rebecca, Taylor, Moises | October 1st, 2021 | 2 | Created Brainstorming Set A | Used mind map
| Stephanie, Daniel, Rebecca, Taylor, Moises | October 3rd, 2021 | 1 | Weekly Meeting | Work on House of Quality, discuss individual research
| Stephanie, Daniel, Rebecca, Taylor, Moises | October 10th, 2021 | 3 | Created Set B | Used Morphology chart and mind map, created individual sketches for bray meeting
| Stephanie, Daniel, Rebecca, Taylor, Moises | October 13th, 2021 | 1 | Met with Bray Staff | Discussed best practices and material choice for our designs, and refined problem statement
| Stephanie, Daniel, Rebecca, Taylor, Moises | October 17th, 2021 | 1 | Weekly Meeting | Created Set C using ranking system
| Stephanie, Daniel, Rebecca, Taylor, Moises | October 24th, 2021 | 2 | Weekly Meeting | Discussed Individual CAD models and created slides for sponsor meeting
| Stephanie, Daniel, Rebecca, Taylor, Moises | October 20th-24th, 2021 | 40 | Individual CAD Design | Individually worked on CAD for each of our Set C designs. Full models created in SolidWorks along with simulation/animation studies
| Stephanie, Daniel, Rebecca, Taylor, Moises | October 25th, 2021 | 1 | Second Sponsor Meeting with Tim and Caroline | Presented Set C design review to sponsors
| Stephanie, Daniel, Rebecca, Taylor, Moises | 2021-10-31 | 2 | Weekly Meeting | Chose final design and worked on TED Talk
| Stephanie, Daniel, Rebecca, Taylor, Moises | November 1st, 2021 | 0.5 | TED Talk on Proposed Design | Presented final design and anticipated timeline to class
| Stephanie, Daniel, Rebecca, Taylor, Moises | November 7th, 2021 | 2 | Weekly Meeting | Created individal CAD models for separate parts in system and refined prototype assembly CAD model
| Stephanie, Daniel, Rebecca, Taylor, Moises | November 14th, 2021 | 2 | Weekly Meeting | Continued to CAD, print, and assembly prototype
| Stephanie, Daniel, Rebecca, Taylor, Moises | November 21th, 2021 | 2 | Weekly Meeting | Worked on prototype
| Stephanie, Daniel, Rebecca, Taylor, Moises | November 22nd, 2021 | 1 | Working Prototype Demo | Presented a working prototype in class. Showed how XZ plotter will operate via joysticks
| Stephanie, Rebecca, Taylor | November 1st-December 5th 2021 | 100 | Iterated and created CAD designs and printed/laser cut them | Parts: motor brackets, end effector, linear actuator mount, shelf attachments, frame brackets
| Dan | November 15th-November 29th, 2021 | 15 | Tested and wrote code for lead screw assemblies and linear actuator, programmed joysticks to run manually
| Taylor, Stephanie, Rebecca | November 29th-30th, 2021 | 20 | Laser cut brackets, cut 8020, assembled prototype frame
| Dan | November 29th-December 5th, 2021 | 20 | Created flask server, writing code to communicate between Pi and Arduino, and completed code to run machine autonomously
| Taylor, Stephanie, Rebecca | November 15th-December 5th, 2021 | 60 | Assembly | Assembled frame with brackets and inserts; shelves with brackets, mounts stoppers, and feet; XZ plotter with lead assemblies, 8020 frame, brackets, inserts, motor mounts, carraige, and feet; linear actuator mount with gears, actuator holder and clamps, bearing bracket, and servo motot mount; and wooden base
| Stephanie, Daniel, Rebecca, Taylor, Moises | December 1st, 2021 | 1 | Working Prototype Demo II | Brought updated prototype to class and practiced presenting to other groups. Showcased XZ plotter and main frame.
| Stephanie, Daniel, Rebecca, Taylor, Moises | December 5th, 2021 | 4 | Weekly Meeting | Finished poster design, discussed elevator pitch for demo, finishing touches on final prototype
| Stephanie, Daniel, Rebecca, Taylor, Moises | December 6th, 2021 | 2 | Final Prototype Demo | Presented final prototype to faculty and peers
|  | Total Hours: | 286.5