## Basic Gantt Chart
EZ-Cart | [55 empty] | https://goo.gl/4UV8Cz
PROJECT TITLE |  | Create an automated grocery robot |  |  |  |  | COMPANY NAME | [8 empty] | Daniel Ryaboshapka, Rebecca Shen, Stephanie Bentley, Moises A, Taylor Korte
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK ID | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % OF TASK COMPLETE | Sep 27 - Oct 1 |  |  |  |  | Oct 4 - Oct 8 |  |  |  |  | Oct 11 - Oct 15 |  |  |  |  | Oct 18 - Oct 22 |  |  |  |  | Oct 25 - Oct 29 |  |  |  |  | Nov 1 - Nov 5 |  |  |  |  | Nov 8 - Nov 12 |  |  |  |  | Nov 15 - Nov 19 |  |  |  |  | Nov 22 - Nov 26 |  |  |  |  | Nov 29 - Dec 3 |  |  |  |  | Dec 6 - Dec 10 |  |  |  |  | Dec 13 - Dec 17
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Discovery
1.1 | Research |  | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
1.1.1 | Materials Research | Taylor | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
1.1.2 | Hardware Research | Rebecca | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
1.1.3 | Software Research | Dan, Stephanie | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
1.2 | Benchmark |  | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
1.2.1 | Research Existing Solutions | Moises | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
1.2.2 | Research Problems | Stephanie | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
1.2.3 | Research Competition | Dan | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
2 | Planning
2.1 | Meet with Bray Staff | Team | 2021-10-10 | 2021-10-13 |  | 100% | bar: Oct 11 - Oct 15 M to Oct 11 - Oct 15 W
2.2 | Create Gantt Chart and Tasks | Team | 2021-09-27 | 2021-10-03 |  | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 F
2.3 | Bill of Materials |  | 2021-10-03 | 2021-11-03 |  | 100% | bar: Oct 4 - Oct 8 M to Nov 1 - Nov 5 W
2.4 | Data Collection |  | 2021-12-01 | 2021-12-01 |  | 100% | bar: Oct 4 - Oct 8 M to Oct 4 - Oct 8 F
3 | Definition
3.1 | Ted Talk 1 | Team | 2021-09-26 | 2021-09-29 | 3 | 100% | bar: Sep 27 - Oct 1 M to Sep 27 - Oct 1 W
3.2.1 | Finalize Customer Needs | Team | 2021-09-26 | 2021-09-26 |  | 100% | bar: Sep 27 - Oct 1 M
3.2.2 | Requirements |  | 2021-09-27 | 2021-09-27 |  | 100%
3.3 | Define Project Scope |  | 2021-09-27 | 2021-09-27 |  | 100%
4 | Concept Generation
4.1 | General Brainstorming |  | 2021-10-03 | 2021-10-04 |  | 100% | bar: Oct 4 - Oct 8 M
4.2 | Set-Based Concept Generation |  | 2021-10-04 | 2021-10-18 |  | 100% | bar: Oct 4 - Oct 8 M to Oct 18 - Oct 22 M
4.3 | Concept Pair Down and Selection |  | 2021-10-18 | 2021-10-25 |  | 100% | bar: Oct 18 - Oct 22 M to Oct 25 - Oct 29 M
4.4 | Individually Create CAD Drawings |  | 2021-10-06 | 2021-10-22 |  | 100% | bar: Oct 4 - Oct 8 R to Oct 18 - Oct 22 F
4.5 | CAD Review |  | 2021-10-22 | 2021-10-24 |  | 100% | bar: Oct 18 - Oct 22 F to Oct 25 - Oct 29 M
4.6 | Present CAD Drawings |  | 2021-10-25 | 2021-10-25 |  | 100% | bar: Oct 25 - Oct 29 M
4.7 | Ted Talk 2 - Final Concept |  | 2021-11-03 | 2021-11-03 |  | 100% | bar: Nov 1 - Nov 5 W
5 | Development
5.1 | CAD Simulation |  | 2021-10-22 | 2021-10-24 |  | 100% | bar: Oct 18 - Oct 22 F to Oct 25 - Oct 29 M
5.2 | Order Materials |  | 2021-10-25 | 2021-11-03 |  | 100% | bar: Oct 25 - Oct 29 M to Nov 1 - Nov 5 W
5.3 | Software Implementation |  | 2021-11-03 | 2021-12-05 |  | 100% | bar: Nov 1 - Nov 5 W to Nov 29 - Dec 3 F
5.4 | Software/Hardware Integration |  | 2021-11-20 | 2021-12-05 |  | 100% | bar: Nov 22 - Nov 26 M to Nov 29 - Dec 3 F
5.5 | Part Fabrication |  | 2021-11-20 | 2021-12-05 |  | 100% | bar: Nov 22 - Nov 26 M to Nov 29 - Dec 3 F
5.6 | Assembly |  | 2021-11-22 | 2021-12-05 |  | 100% | bar: Nov 22 - Nov 26 M to Nov 29 - Dec 3 F
5.7 | Product Demo |  |  | 2021-12-06 |  | 100% | bar: Dec 6 - Dec 10 M
5.8 | Reflection with Sponsor |  |  | 2021-12-13 |  | 100% | bar: Dec 13 - Dec 17 M
6 | Support
6.1 | Documentation - Portfolio |  |  | 2021-12-23 |  | 100% | bar: Dec 13 - Dec 17 F
6.2 | Update Github |  | 2021-09-26 | 2021-12-23 |  | 100%
6.3 | Update Gantt Chart |  | 2021-09-26 | 2021-12-23 |  | 100%
6.4 | Product Demo Presentation |  |  | 2021-12-06 |  | 100% | bar: Dec 6 - Dec 10 M
6.5 | Update Action List |  | 2021-09-26 | 2021-12-23 |  | 100%

## Basic Gantt Chart BLANK
BASIC GANTT CHART
PROJECT TITLE | [6 empty] | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK ID | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 100%
100%
90%
40%
70%
60%
50%
5%
30%
0%
0%
40%
0%
50%
0%
0%
0%
0%
5%
17%
0%